## Start Here
EU AI Compass
EU AI Act Deployer Obligations Checklist
A practical checklist for mapping deployer obligations to owners, evidence artifacts, status, and next actions.
Branding placeholder | Insert EU AI Compass icon/logo in this area before publishing.
SEO file name | eu-ai-act-deployer-obligations-checklist.xlsx
Primary keyword | EU AI Act deployer obligations checklist
Workbook scope | Deployer obligation tracking, evidence planning, owner assignment, Article 4, Article 26, Article 27, and Article 50 readiness.
Last updated | 2026-04-28
How to use | 1. Start on the main worksheet. 2. Replace example rows with your organization’s data. 3. Use drop-downs consistently. 4. Add evidence links or file references. 5. Review with legal, compliance, security, and business owners before relying on the outputs.
Included sheets | Start Here ¦ Dashboard ¦ Deployer Checklist ¦ Lookups ¦ Sources ¦ Review Notes
Legal / compliance note | Operational readiness worksheet only. Not legal advice, not a conformity assessment, and not a guarantee of EU AI Act compliance. Validate legal interpretation with qualified counsel.
#VALUE!

## Dashboard
EU AI Act Deployer Obligations Dashboard
Use this dashboard to focus on high-priority obligations, open evidence gaps, and owner accountability.
KPI | Formula | Result | Priority / status view | Count
Checklist items |  | 58 | Critical priority | 3
Open items |  | 5 | High priority | 4
Blocked items |  | 0 | Not started | 0
Review required |  | 1 | Review required | 1

## Deployer Checklist
EU AI Act Deployer Obligations Checklist
Map deployer obligations to owners, evidence artifacts, current state, and remediation actions.
Item ID | Workstream | AI Act Reference | Obligation / Activity | Applies To | Trigger Condition | Evidence Artifact | Owner Role | Current State | Priority | Due Date | Status | Evidence Location / Link | Notes
DEP-001 | AI literacy | Article 4 | Define AI literacy expectations for staff and contractors involved with AI systems. | Providers and deployers | Any organizational use of AI systems | AI literacy matrix, training records, attendance evidence | HR / Compliance | Not assessed | High |  | Open |  | Applies broadly. Validate role-specific literacy requirements.
DEP-002 | Use according to instructions | Article 26 | Retain provider instructions and confirm the system is used within the documented intended purpose. | Deployers of high-risk AI systems | High-risk system in use or planned | Provider instructions, operating procedure, sign-off record | System Owner | Not assessed | Critical |  | Open |  | Confirm legal scope before treating system as high-risk.
DEP-003 | Human oversight | Article 26 | Assign trained human oversight owner and document override/escalation points. | Deployers of high-risk AI systems | High-risk AI used in business process | Oversight procedure, escalation log, reviewer training record | Business Owner | Partial | Critical |  | In Progress |  | Oversight must be operational, not only a policy statement.
DEP-004 | Input data governance | Article 26 | Verify input data is relevant and sufficiently representative for the intended use where deployer controls input data. | Deployers of high-risk AI systems | Deployer controls or supplies input data | Input data checklist, data owner approval, data quality notes | Data Owner | Not assessed | High |  | Open |  | Coordinate with DPO/privacy team where personal data is involved.
DEP-005 | Monitoring and incident escalation | Article 26 | Monitor system operation and define escalation when performance, misuse, or risk indicators appear. | Deployers of high-risk AI systems | Live high-risk AI system | Monitoring log, issue register, escalation procedure | Operations Owner | Not assessed | High |  | Open |  | Align with incident response and vendor management process.
DEP-006 | Log retention | Article 26 | Retain logs where under deployer control and define review access. | Deployers of high-risk AI systems | System generates logs available to deployer | Log retention schedule, access control record | IT / Security | Not assessed | Medium |  | Open |  | Verify technical feasibility and retention period with counsel.
DEP-007 | FRIA scoping | Article 27 | Determine whether a Fundamental Rights Impact Assessment is required before deployment. | Certain deployers of high-risk AI systems | Public body or specified private-sector use case | FRIA scoping note, FRIA worksheet, approval record | Compliance / Legal | Not assessed | Critical |  | Review Required |  | Do not assume all deployers have the same FRIA obligation.
DEP-008 | Transparency notices | Article 50 | Determine whether AI interaction, synthetic content, or other transparency notice is required. | Providers and deployers depending on use case | User-facing AI interaction or synthetic/generated content | Notice template, placement screenshot, approval record | Product Owner | Partial | High |  | In Progress |  | Map notice placement to the actual user journey.
DEP-009
DEP-010
DEP-011
DEP-012
DEP-013
DEP-014
DEP-015
DEP-016
DEP-017
DEP-018
DEP-019
DEP-020
DEP-021
DEP-022
DEP-023
DEP-024
DEP-025
DEP-026
DEP-027
DEP-028
DEP-029
DEP-030
DEP-031
DEP-032
DEP-033
DEP-034
DEP-035
DEP-036
DEP-037
DEP-038
DEP-039
DEP-040
DEP-041
DEP-042
DEP-043
DEP-044
DEP-045
DEP-046
DEP-047
DEP-048
DEP-049
DEP-050
DEP-051
DEP-052
DEP-053
DEP-054
DEP-055
DEP-056
DEP-057
DEP-058

## Lookups (hidden)
Priority
Value | Operational meaning
Critical | Potential go-live blocker or high legal/regulatory exposure.
High | Important control or evidence gap requiring near-term owner action.
Medium | Material but not immediately blocking.
Low | Useful improvement or hygiene item.
Status
Value | Operational meaning
Not Started | No meaningful work started.
Open | Gap identified but not yet remediated.
In Progress | Owner assigned and remediation underway.
Complete | Evidence available and reviewed.
Blocked | Cannot proceed due to dependency.
Review Required | Needs legal, compliance, or executive decision.

## Sources
Source | URL | Use in workbook
Regulation (EU) 2024/1689 official text | https://eur-lex.europa.eu/legal-content/EN/TXT/?uri=CELEX:32024R1689 | Primary legal text for article and annex references
European Commission AI Act entry into force notice | https://commission.europa.eu/news/ai-act-enters-force-2024-08-01_en | General timeline and regulatory context
European Commission AI Act Service Desk Article 113 | https://ai-act-service-desk.ec.europa.eu/en/ai-act/article-113 | Application timeline references
EU AI Act Service Desk Article 26 | https://ai-act-service-desk.ec.europa.eu/en/ai-act/article-26 | Deployer obligations reference
EU AI Act Service Desk Article 27 | https://ai-act-service-desk.ec.europa.eu/en/ai-act/article-27 | FRIA reference
EU AI Act Service Desk Article 50 | https://ai-act-service-desk.ec.europa.eu/en/ai-act/article-50 | Transparency obligations reference

## Review Notes
Review Date | Reviewer | Area Reviewed | Finding / Decision | Action Owner | Target Date | Status | Notes
|  | Legal interpretation |  |  |  | Open
|  | Business owner review |  |  |  | Open
|  | Security / privacy review |  |  |  | Open
|  | Evidence completeness |  |  |  | Open